SmartMoney

Go-Live Overview

Status, order of work and the map of the go-live manuals

For: Rupankar (owner), Sujay and Tushar (Shuru)

Version: 1.0, 18 October 2026

Prepared by: Shuru (Sujay and Tushar), for the SmartMoney business

Contents

1. The plan in one page

2. Where things stand today

3. The 7-day schedule: 20 to 27 October 2026

4. Decisions still open

5. The manuals

6. Rules for everyone

# 1. The plan in one page

SmartMoney goes live in four stages. Rupankar, the owner, does only the steps that need his identity, documents or payment card. Shuru, the developers, does everything technical through access Rupankar grants. Every account, bill and store listing stays in the SmartMoney business name.

| Stage | What happens | Who | Manual |
| --- | --- | --- | --- |
| A. Accounts | D-U-N-S number, Google Play developer account, Azure access for Shuru, Brevo team members | Rupankar | 01 Owner Guide |
| B. Server | Database, image storage and API on Azure at api.smart-money.in; sign-up emails through Brevo | Shuru | 02 Azure Server Guide |
| C. Apps | Final names and icons, signing keys, release builds, test tracks on Google Play | Shuru | 03 Play Store Guide |
| D. Test and launch | Rupankar tests on his phone, approves, and the user app is sent for Google review | Both | 01 Owner Guide (Part 9), 03 Play Store Guide |
| Extra. Notifications | Push notifications for cashback and withdrawals, built while the D-U-N-S number is pending | Shuru, with one Firebase step by Rupankar | 04 Push Notifications Guide |

# 2. Where things stand today

| Item | Status | Next action | Owner |
| --- | --- | --- | --- |
| App code (user app, admin app, server) | Built and tested: 703 server tests, 107 user-app tests, 289 admin-app tests pass. Final IDs, names and icons applied on 20 October | Release builds once the Android SDK is installed | Shuru |
| App names and IDs | Approved and applied: "SmartMoney" (in.smartmoney.app) and "SmartMoney Admin" (in.smartmoney.admin) | None | Done |
| Azure account | Created with Rupankar's Gmail and debit card; Shuru uses the owner login | Set a spending alert (Owner Guide, Part 5) | Rupankar |
| Azure resources (database, storage, API) | Not created yet; scripts are ready | Run the Azure Server Guide | Shuru |
| Domain smart-money.in | Bought on GoDaddy; a static website by another developer is live; Shuru has the GoDaddy login | Add the two records for api.smart-money.in after the server is created | Shuru |
| D-U-N-S number | Rupankar is looking into it | Request it this week (Owner Guide, Part 1) | Rupankar |
| Google Play developer account | Not created | Create as Organisation (Owner Guide, Part 3) | Rupankar |
| Brevo (email for sign-up codes) | Signed up, configured and tested: sign-up codes arrive | Use the same SMTP login and sender address in the production settings | Shuru |
| Cuelinks live account | Signed up by Rupankar; Shuru has the login | Create the V3 API key, set the Global Postback (Azure Server Guide, Step 13) | Shuru |
| Cuelinks tracking in the code | Written and tested on 20 October against the official V3 API (tracked links with sub ID, postbacks in Cuelinks' formats, payable status) | Switch on with the API key and prove with one real purchase | Shuru |
| Push notifications | Not built | Firebase project, then build (Notifications Guide) | Shuru |
| Signing keys | Not created | Create and hand a copy to Rupankar (Play Store Guide) | Shuru |
| Android build tools on Shuru's PC | Not installed | Install Android Studio (Play Store Guide, Part B) | Shuru |
| Privacy policy and account-deletion pages | Added to the server; go live with the Azure deploy | Replace the Cashfree wording before Google review | Shuru, wording approved by Rupankar |

# 3. The 7-day schedule: 20 to 27 October 2026

Everything Shuru controls is finished by 27 October: the server live on Azure, both apps built and signed, and both on Google Play test tracks if the Play account is verified by 23 October. The public store listing date is set by D&B and Google, so it is not promised for 27 October.

| Day | Rupankar | Shuru (using the owner logins for Azure, GoDaddy and Cuelinks) |
| --- | --- | --- |
| Tue 20 | Email D&B for the D-U-N-S number (Owner Guide, Part 1: the website form is down). Start the Play sign-up as an organisation. | Commit the work so far (done). Create the Cuelinks V3 API key and a sample link with a sub ID. Install Android Studio. Create both signing keys. |
| Wed 21 | Chase D&B if no reply. | Build the Azure server and deploy the API. Add the two GoDaddy records for api.smart-money.in. Claude writes the Cuelinks link and postback code. |
| Thu 22 | Approve the new payout wording for the privacy policy and terms. | Set up the Cuelinks Global Postback and test it. Release builds. Check the admin app on a phone. |
| Fri 23 | Finish Play verification when the D-U-N-S number arrives. Invite Sujay and Tushar. | Play Console: both apps, forms, listing, screenshots (prepared offline if the account is not ready). |
| Sat 24 | Install the test builds and test (Owner Guide, Part 9). | Upload: user app to internal testing, admin app to closed testing. |
| Sun 25 | One real purchase through the app. | Fixes and a new build. Confirm the purchase shows as pending cashback. |
| Mon 26 | Approve the listing. | Spare day for fixes. |
| Tue 27 |  | Send the user app for Google review. Decide the fallback if there is still no D-U-N-S number. |

Push notifications move to the first update after launch, so they do not hold up the week.

## If a wait runs long

The slowest steps are outside our control: the D-U-N-S number (D&B), Play account verification and app review (Google). The table below is the original order of work, which still applies if those take longer.

| When | Rupankar | Shuru |
| --- | --- | --- |
| Week 1 | Request D-U-N-S. Give Azure access. Add Brevo team members. Ask Cuelinks for API access and the postback details. | Build the Azure server. Install Android Studio. Create signing keys. Apply app names and icons. Start push notifications. |
| When Cuelinks replies | Pass the API key and channel ID to Shuru securely. Paste the postback address Shuru sends into Cuelinks. | Finish the Cuelinks link and postback code. Test one real purchase end to end. |
| When D-U-N-S arrives | Create the Play developer account. Invite Sujay and Tushar. | Create both apps in Play Console. Fill the forms (privacy, data safety, rating). |
| About 1 week later | Install the test versions and test them (Part 9 of the Owner Guide). Approve. | Upload builds to internal testing (user app) and closed testing (admin app). Fix what Rupankar finds. |
| Launch | Approve the listing. | Send the user app for Google review. Release to India. |

Important  Google reviews a new app for a few days, sometimes longer. Do not announce a launch date until the review has passed.

Important  Do not launch publicly until one real purchase made through the app has shown up as cashback. Until the Cuelinks API key is set, purchases earn no commission.

# 4. Decisions still open

| Decision | Proposal | Why it matters |
| --- | --- | --- |
| Permanent app IDs | Decided 20 October: in.smartmoney.app and in.smartmoney.admin | They can never change after the first upload. |
| Google account that owns Play Console | A business email (for example an address on smart-money.in) or a new Gmail used only for the business | Never a personal Gmail: the business must not depend on one person's account. |
| Push notifications in the first release? | Yes if ready before the D-U-N-S number; otherwise the first update | Not required by Google; useful for users. |

# 5. The manuals

| File | For | What it covers |
| --- | --- | --- |
| 00 Overview (this file) | Everyone | Status, order of work, open decisions |
| 01 Owner Guide | Rupankar | D-U-N-S, Play account, Azure access, GoDaddy DNS, Brevo, Cuelinks, testing manual, approval |
| 02 Azure Server Guide | Shuru | Database, storage, API, domain, email, checks, updates |
| 03 Play Store Guide | Shuru | Build tools, IDs, signing keys, Play Console forms, test tracks, production release |
| 04 Push Notifications Guide | Shuru, with one step for Rupankar | Firebase setup, what gets built, testing, Play form changes |

# 6. Rules for everyone

- Secrets never go in chat groups or the code. Passwords, keys and API keys are shared through a password manager or in person.

- Rupankar keeps a copy of everything: logins, the two signing key files and their passwords.

- The existing website on smart-money.in is not touched. Shuru only adds records for new subdomains such as api.smart-money.in.

- Nothing is deployed or uploaded without the step before it passing. Each manual ends a step with a "Done when" check.